## Sheet1
Start Date | 2023-12-01 |  | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14 | Day15
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Task | StartDate | End Date | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday
Requirement Analysis | 2023-11-01 | 2023-11-03 | bar: Day1 1 to Day3 3
Web Hosting / Domain | 2023-11-04 | 2023-11-05 | bar: Day4 4 to Day5 5
Server File Setup in Local Host | 2023-11-06 | 2023-11-07 | bar: Day6 6 to Day7 7
Home Page Design | 2023-11-08 | 2023-11-09 | bar: Day8 8 to Day9 9
Page Design | 2023-11-10 | 2023-11-12 | bar: Day10 10 to Day12 12
Contact Page Design | 2023-11-13 | 2023-11-13 | bar: Day13 13
Add Product | 2023-11-14 | 2023-11-14 | bar: Day14 14
Payment gateway in integration | 2023-11-15 | 2023-11-15 | bar: Day15 15
Footer setup | 2023-11-15 | 2023-11-15 | bar: Day15 15
Website Live on Hosting | 2023-11-15 | 2023-11-15 | bar: Day15 15
Testing | 2023-11-15 | 2023-11-16 | bar: Day15 15